## original plan
Planning
Project: |  | Design of a walking robot
Project group: |  | Yellow production Ltd |  | Date: |  | 2011-01-15 | [6 empty] | Reviewed:
Customer: |  | Tomas Svensson |  | Version: |  | 1
Course: |  | Elektronics project Y |  | Author: |  | Pelle
ACTIVITIES |  |  | TIME | WHO | TIME PLAN (week number)
No | Description |  | Hours | Initials | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 24 | 26
1 | write requirement specification |  | 40 | all | 10 | 20 | 10 | [20 empty] | 40
2 | make a system drawing |  | 15 | aa,kk,oo,ss |  |  | 10 | 5 | [19 empty] | 15
3 | write a project plan |  | 100 | all |  |  |  | 20 | 20 | 20 | 20 |  | 20 | [14 empty] | 100
4 | identify activities |  | 8 | aa,kk |  |  |  |  | 8 | [18 empty] | 8
5 | estimate time of activities |  | 8 | all |  |  |  |  | 4 | 4 | [17 empty] | 8
6 | resource allocation |  | 4 | all | [6 empty] | 4 | E |  |  | E | E | E | [7 empty] | E |  | H | 4
7 | make a timeplan |  | 16 | pp | [7 empty] | X | 16 |  | X | X | X | [7 empty] | X |  | O | 16
8 | read more about xx |  | 12 | pp,ss |  |  | 6 | 6 |  |  |  | A |  |  | A | A | A | [7 empty] | A |  | L | 12
9 | investigate technology yy |  | 20 | oo,kk |  |  |  | 10 | 5 | 3 | 2 | M |  |  | M | M | M | [7 empty] | M |  | I | 20
10 | write design spec for subsystem1 |  | 30 | aa,kk | [7 empty] | I | 20 | 10 | I | I | I | [7 empty] | I |  | D | 30
11 | write design spec for subsystem2 |  | 20 | oo,ss | [7 empty] | N |  | 10 | N | N | N | 10 | [6 empty] | N |  | A | 20
12 | modify the project pplan |  | 4 | pp | [7 empty] | A |  |  | A | A | A | 4 | [6 empty] | A |  | Y | 4
13 | design subsystem 1 |  | 60 | aa,kk | [7 empty] | T |  | 20 | T | T | T | 10 | 10 | 10 | 10 |  |  |  | T |  | S | 60
14 | design subsystem 2 |  | 100 | oo,ss | [7 empty] | I |  |  | I | I | I | 20 | 20 | 20 | 20 | 10 | 10 |  | I |  |  | 100
15 | integrate and test |  | 30 | all | [7 empty] | O |  |  | O | O | O |  |  |  |  | 20 | 10 |  | O |  |  | 30
16 | write product documentation |  | 60 | pp | [7 empty] | N |  | 10 | N | N | N | 5 | 5 | 10 | 10 | 10 | 10 |  | N |  |  | 60
17 | make a project evaluation |  | 4 | all | [19 empty] | 4 |  |  |  | 4
18 | project meetings |  | 49 | all |  | 7 |  | 7 |  | 7 |  | P |  | 7 | P | P | P | 7 |  | 7 |  | 7 |  |  | P |  |  | 49
19 | milestone 1, requirement specification ready | [5 empty] | fr |  |  |  |  | E |  |  | E | E | E | [7 empty] | E |  |  | 0
20 | milestone 2, project plan ready | [10 empty] | R | th |  | R | R | R | [7 empty] | R |  |  | 0
21 | milestone 3, designspecifications ready | [10 empty] | I |  |  | I | I | I | fr | [6 empty] | I |  |  | 0
22 | milestone 4, subsystem ready | [10 empty] | O |  |  | O | O | O |  |  | th |  |  |  |  | O |  |  | 0
23 | milestone 5, all delivearables ready | [10 empty] | D |  |  | D | D | D | [5 empty] | fr |  | D |  |  | 0
24 | tollgate 1, acceptance of requirement specification | [6 empty] | we | [19 empty] | 0
25 | tollgate 2, acceptance of project plan | [11 empty] | fr | [14 empty] | 0
26 | tollgate 5, acceptance of delivery | [21 empty] | fr |  |  |  |  | 0
| Total number of hours |  | 580 |  | 10 | 27 | 26 | 48 | 37 | 34 | 26 | 0 | 56 | 57 | 0 | 0 | 0 | 56 | 35 | 47 | 40 | 47 | 30 | 4 | 0 | 0 | 0 | 580

## Summing of time
SUMMING OF TIME
Project: |  | Design of a walking robot
Project group: |  | Yellow production Ltd | Date: |  | 2011-02-22 | [6 empty] | Reviewed:
Customer: |  | Tomas Svensson | Version: |  | 1.7
Course: |  | Elektronics project Y | Author: |  | Pelle
RESOURCE |  |  |  | USED TIME (per week)
| Name |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 24 | 26 | Su
| Anna Andersson |  |  | 5 | 2 | 3 | 5 | 4 | 2 | 1 | 2 | 1 | [14 empty] | 25
| Kalle Karlsson |  |  | 3 | 10 | 2 | 3 | 8 | 4 | 2 |  | 5 | [14 empty] | 37
| Olle Olsson |  |  | 5 | 8 | 5 | 8 | 9 | 1 | 5 |  | 2 | [14 empty] | 43
| Pelle Perssson (project manager) |  |  | 4 | 4 | 5 | 4 | 5 | 3 | 2 | 4 | 4 | [14 empty] | 35
| Stina Svensson |  |  | 8 | 6 | 7 | 4 | 3 | 6 | 6 |  | 3 | [14 empty] | 43
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total number of hours: |  |  | 25 | 30 | 22 | 24 | 29 | 16 | 16 | 6 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183