## Original plan
Original plan
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date: |  | 2011-08-13 | [6 empty] | Reviewed:
Customer: |  | Tomas Svensson |  | Version: |  | 1
Course: |  | Electronics project |  | Author: |  | kk
ACTIVITIES |  |  | TIME | who | TIME PLAN (week number)
No | Description |  | Hours | Initials | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | requirement specification |  | 23 | all | 10 | 13 | [21 empty] | 23
2 | time plan |  | 40 | aa,kk,oo,ss |  |  | 15 | 25 | [19 empty] | 40
3 | resource plan |  | 12 | kk,oo |  |  |  | 12 | [19 empty] | 12
4 | test specification |  | 10 | ss |  |  |  |  | 10 | [18 empty] | 10
5 | design |  | 110 | all | 10 | 10 | 20 | 20 | 20 | 30 | [17 empty] | 110
6 | activity 1 |  | 13 | ss | [5 empty] | 5 | 8 | [16 empty] | 13
7 | activity 2 |  | 90 | aa,kk,oo,ss | [7 empty] | 40 | 50 | [14 empty] | 90
8 | activity 3 |  | 120 | oo |  |  |  |  | 10 | 20 | 20 | 50 | 20 | [14 empty] | 120
9 | activity 4 |  | 45 | aa | [8 empty] | 20 | 25 | [13 empty] | 45
10 | [27 empty] | 0
11 | [27 empty] | 0
12 | [27 empty] | 0
13 | [27 empty] | 0
14 | [27 empty] | 0
15 | project meetings |  | 25 |  |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 | [13 empty] | 25
16 | [27 empty] | 0
17 | [27 empty] | 0
18 | [27 empty] | 0
19 | milestone 1 | [5 empty] | fr | [20 empty] | 0
20 | milestone 2 | [11 empty] | th | [14 empty] | 0
21 | milestone 3 | [14 empty] | tu | [11 empty] | 0
22 | milestone 4 | [18 empty] | th | [7 empty] | 0
23 | milestone 4 | [24 empty] | fr |  | 0
24 | tollgate 1 | [6 empty] | we | [19 empty] | 0
25 | tollgate 2 | [11 empty] | we | [14 empty] | 0
26 | tollgate 3 | [25 empty] | we | 0
27 | [27 empty] | 0
28 | [27 empty] | 0
29 | [27 empty] | 0
30 | [27 empty] | 0
31 | [27 empty] | 0
32 | [27 empty] | 0
33 | [27 empty] | 0
34 | [27 empty] | 0
35 | [27 empty] | 0
36 | [27 empty] | 0
37 | [27 empty] | 0
38 | [27 empty] | 0
39 | [27 empty] | 0
40 | [27 empty] | 0
41 | [27 empty] | 0
42 | [27 empty] | 0
43 | [27 empty] | 0
44 | [27 empty] | 0
45 | [27 empty] | 0
46 | [27 empty] | 0
47 | [27 empty] | 0
48 | [27 empty] | 0
49 | [27 empty] | 0
50 | [27 empty] | 0
51 | [27 empty] | 0
52 | [27 empty] | 0
53 | [27 empty] | 0
54 | [27 empty] | 0
55 | [27 empty] | 0
56 | [27 empty] | 0
57 | [27 empty] | 0
58 | [27 empty] | 0
59 | [27 empty] | 0
60 | [27 empty] | 0
61 | [27 empty] | 0
62 | [27 empty] | 0
63 | [27 empty] | 0
64 | [27 empty] | 0
65 | [27 empty] | 0
66 | [27 empty] | 0
67 | [27 empty] | 0
68 | [27 empty] | 0
69 | [27 empty] | 0
70 | [27 empty] | 0
71 | [27 empty] | 0
72 | [27 empty] | 0
73 | [27 empty] | 0
74 | [27 empty] | 0
75 | [27 empty] | 0
| Total number of hours: |  | 488 |  | 20 | 28 | 35 | 62 | 40 | 60 | 28 | 95 | 90 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488

## Modified plan
Modified plan
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date: |  | 2011-09-22 | [6 empty] | Reviewed
Customer: |  | Tomas Svensson |  | Version |  | 1.1
Course: |  | Electronics project |  | Author: |  | kk
ACTIVITIES |  |  | TIME | WHO | TIME PLAN (week number)
No | Description |  | hours | Initials | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | requirement specification |  | 23 | all | 10 | 13 | [21 empty] | 23
2 | time plan |  | 40 | aa,kk,oo,ss |  |  | 15 | 25 | [19 empty] | 40
3 | resource plan |  | 12 | kk,oo |  |  |  | 12 | [19 empty] | 12
4 | test specification |  | 10 | ss |  |  |  |  | 10 | [18 empty] | 10
5 | design |  | 110 | all | 10 | 10 | 20 | 20 | 20 | 30 | [17 empty] | 110
6 | activity 1 |  | 13 | ss | [5 empty] | 5 | 8 | [16 empty] | 13
7 | activity 2 |  | 90 | aa,kk,oo,ss | [7 empty] | 40 | 50 | [14 empty] | 90
8 | activity 3 |  | 110 | oo |  |  |  |  | 10 | 20 | 20 | 50 | 10 | [14 empty] | 110
9 | activity 4 |  | 45 | aa | [8 empty] | 20 | 25 | [13 empty] | 45
10 | 0 |  | 40 | kk,oo | [8 empty] | 10 | 10 | 10 | 10 | [11 empty] | 40
11 | 0 |  | 25 | ss | [10 empty] | 5 | 10 | 10 | [10 empty] | 25
12 | 0 | [26 empty] | 0
13 | 0 | [26 empty] | 0
14 | 0 | [26 empty] | 0
15 | project meetings |  | 25 |  |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 | [13 empty] | 25
16 | 0 | [26 empty] | 0
17 | 0 | [26 empty] | 0
18 | 0 | [26 empty] | 0
19 | milestone 1 | [5 empty] | fr | [20 empty] | 0
20 | milestone 2 | [11 empty] | th | [14 empty] | 0
21 | milestone 3 | [14 empty] | tu | [11 empty] | 0
22 | milestone 4 | [18 empty] | th | [7 empty] | 0
23 | milestone 4 | [24 empty] | fr |  | 0
24 | tollgate 1 | [6 empty] | we | [19 empty] | 0
25 | tollgate 2 | [11 empty] | we | [14 empty] | 0
26 | tollgate 3 | [25 empty] | we | 0
27 | 0 | [26 empty] | 0
28 | 0 | [26 empty] | 0
29 | 0 | [26 empty] | 0
30 | 0 | [26 empty] | 0
31 | 0 | [26 empty] | 0
32 | 0 | [26 empty] | 0
33 | 0 | [26 empty] | 0
34 | 0 | [26 empty] | 0
35 | 0 | [26 empty] | 0
36 | 0 | [26 empty] | 0
37 | 0 | [26 empty] | 0
38 | 0 | [26 empty] | 0
39 | 0 | [26 empty] | 0
40 | 0 | [26 empty] | 0
41 | 0 | [26 empty] | 0
42 | 0 | [26 empty] | 0
43 | 0 | [26 empty] | 0
44 | 0 | [26 empty] | 0
45 | 0 | [26 empty] | 0
46 | 0 | [26 empty] | 0
47 | 0 | [26 empty] | 0
48 | 0 | [26 empty] | 0
49 | 0 | [26 empty] | 0
50 | 0 | [26 empty] | 0
51 | 0 | [26 empty] | 0
52 | 0 | [26 empty] | 0
53 | 0 | [26 empty] | 0
54 | 0 | [26 empty] | 0
55 | 0 | [26 empty] | 0
56 | 0 | [26 empty] | 0
57 | 0 | [26 empty] | 0
58 | 0 | [26 empty] | 0
59 | 0 | [26 empty] | 0
60 | 0 | [26 empty] | 0
61 | 0 | [26 empty] | 0
62 | 0 | [26 empty] | 0
63 | 0 | [26 empty] | 0
64 | 0 | [26 empty] | 0
65 | 0 | [26 empty] | 0
66 | 0 | [26 empty] | 0
67 | 0 | [26 empty] | 0
68 | 0 | [26 empty] | 0
69 | 0 | [26 empty] | 0
70 | 0 | [26 empty] | 0
71 | 0 | [26 empty] | 0
72 | 0 | [26 empty] | 0
73 | 0 | [26 empty] | 0
74 | 0 | [26 empty] | 0
75 | 0 | [26 empty] | 0
| Total number of hours: |  | 543 |  | 20 | 28 | 35 | 62 | 40 | 60 | 28 | 95 | 90 | 40 | 15 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543

## Stina
Used time for person 1
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date: |  |  |  | 2011-09-22
Customer: |  | Tomas Svensson |  | Author: |  |  |  | Stina
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification |  | 1 | 3 | [21 empty] | 4
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design |  | 2 | 1 | [21 empty] | 3
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings |  |  | 1 | [21 empty] | 1
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8

## Olle
Used time for person 2
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date: |  |  |  | 2011-09-22
Customer: |  | Tomas Svensson |  | Author: |  |  |  | Olle
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification |  | 2 | 3 | [21 empty] | 5
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design |  | 3 | 2 | [21 empty] | 5
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings |  |  | 1 | [21 empty] | 1
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11

## Anna
Used time for person 3
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date: |  |  |  | 2011-09-22
Customer: |  | Tomas Svensson |  | Author: |  |  |  | Anna
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification |  | 4 | 1 | [21 empty] | 5
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design |  | 4 | 1 | [21 empty] | 5
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings |  |  | 1 | [21 empty] | 1
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11

## Kalle
Used time for person 4
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date: |  |  |  | 2011-09-22
Customer: |  | Tomas Svensson |  | Author: |  |  |  | Kalle
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification |  | 2 | 5 | [21 empty] | 7
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design |  | 2 | 5 | [21 empty] | 7
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings |  |  | 1 | [21 empty] | 1
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 4 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15

## P5
Used time for person 5
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date:
Customer: |  | Tomas Svensson |  | Author:
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification | [24 empty] | 0
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design | [24 empty] | 0
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings | [24 empty] | 0
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P6
Used time for person 6
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date:
Customer: |  | Tomas Svensson |  | Author:
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification | [24 empty] | 0
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design | [24 empty] | 0
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings | [24 empty] | 0
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P7
Used time for person 7
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date:
Customer: |  | Tomas Svensson |  | Author:
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification | [24 empty] | 0
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design | [24 empty] | 0
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings | [24 empty] | 0
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P8
Used time for person 8
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date:
Customer: |  | Tomas Svensson |  | Author:
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification | [24 empty] | 0
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design | [24 empty] | 0
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings | [24 empty] | 0
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## p9
Used time for person 9
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date:
Customer: |  | Tomas Svensson |  | Author:
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification | [24 empty] | 0
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design | [24 empty] | 0
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings | [24 empty] | 0
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P10
Used time for person 10
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date:
Customer: |  | Tomas Svensson |  | Author:
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification | [24 empty] | 0
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design | [24 empty] | 0
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings | [24 empty] | 0
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summing of TIME
Summing of time
Project: |  | A walking robot
Project group: |  | Team 3 |  | Date:
Customer |  | Tomas Svensson |  | Author:
Course: |  | Electronics project
Activity |  |  | USED TIME (per week)
| Description |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Su
1 | requirement specification |  | 9 | 12 | [21 empty] | 21
2 | time plan | [24 empty] | 0
3 | resource plan | [24 empty] | 0
4 | test specification | [24 empty] | 0
5 | design |  | 11 | 9 | [21 empty] | 20
6 | activity 1 | [24 empty] | 0
7 | activity 2 | [24 empty] | 0
8 | activity 3 | [24 empty] | 0
9 | activity 4 | [24 empty] | 0
10 | 0 | [24 empty] | 0
11 | 0 | [24 empty] | 0
12 | 0 | [24 empty] | 0
13 | 0 | [24 empty] | 0
14 | 0 | [24 empty] | 0
15 | project meetings |  |  | 4 | [21 empty] | 4
16 | 0 | [24 empty] | 0
17 | 0 | [24 empty] | 0
18 | 0 | [24 empty] | 0
19 | milestone 1 | [24 empty] | 0
20 | milestone 2 | [24 empty] | 0
21 | milestone 3 | [24 empty] | 0
22 | milestone 4 | [24 empty] | 0
23 | milestone 4 | [24 empty] | 0
24 | tollgate 1 | [24 empty] | 0
25 | tollgate 2 | [24 empty] | 0
26 | tollgate 3 | [24 empty] | 0
27 | 0 | [24 empty] | 0
28 | 0 | [24 empty] | 0
29 | 0 | [24 empty] | 0
30 | 0 | [24 empty] | 0
31 | 0 | [24 empty] | 0
32 | 0 | [24 empty] | 0
33 | 0 | [24 empty] | 0
34 | 0 | [24 empty] | 0
35 | 0 | [24 empty] | 0
36 | 0 | [24 empty] | 0
37 | 0 | [24 empty] | 0
38 | 0 | [24 empty] | 0
39 | 0 | [24 empty] | 0
40 | 0 | [24 empty] | 0
41 | 0 | [24 empty] | 0
42 | 0 | [24 empty] | 0
43 | 0 | [24 empty] | 0
44 | 0 | [24 empty] | 0
45 | 0 | [24 empty] | 0
46 | 0 | [24 empty] | 0
47 | 0 | [24 empty] | 0
48 | 0 | [24 empty] | 0
49 | 0 | [24 empty] | 0
50 | 0 | [24 empty] | 0
51 | 0 | [24 empty] | 0
52 | 0 | [24 empty] | 0
53 | 0 | [24 empty] | 0
54 | 0 | [24 empty] | 0
55 | 0 | [24 empty] | 0
56 | 0 | [24 empty] | 0
57 | 0 | [24 empty] | 0
58 | 0 | [24 empty] | 0
59 | 0 | [24 empty] | 0
60 | 0 | [24 empty] | 0
61 | 0 | [24 empty] | 0
62 | 0 | [24 empty] | 0
63 | 0 | [24 empty] | 0
64 | 0 | [24 empty] | 0
65 | 0 | [24 empty] | 0
66 | 0 | [24 empty] | 0
67 | 0 | [24 empty] | 0
68 | 0 | [24 empty] | 0
69 | 0 | [24 empty] | 0
70 | 0 | [24 empty] | 0
71 | 0 | [24 empty] | 0
72 | 0 | [24 empty] | 0
73 | 0 | [24 empty] | 0
74 | 0 | [24 empty] | 0
75 | 0 | [24 empty] | 0
| Total number of hours: |  | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45